## 1.Work Plan (Example - Develop)
Project Name/ Goal: | (Example) Improve water quality in yellow creek by developing small robot boat technology to clear blue/green algae from water ways.
TraNsfoRM! Innovation concept: | (Example) Develop and test a ‘fit-for-purpose’ small robot boat to clear blue/green algae faster than existing human methods can.
Develop and test a ‘fit-for-purpose’ small robot boat to clear blue/green algae faster than existing human methods can. | Project Outcome | Concept Readiness Level | Milestone | Activity | JJ 19 activity | JD 19 activity | JJ 20 activity | JD 20 activity | JJ 21 activity | JD 21 activity | JJ 22 activity | Assumptions | Key Evaluation Questions | Analysis / Evidence | UNIQUE VALUES
WATER | Develop and test a ‘fit-for-purpose’ small robot boat to clear blue/green algae faster than existing human methods can. | CRL 1: Initial idea and problem identification | A.1.1 Develop the hypothesis for the clearing of blue green algae for the yellow river catchment including addressing causal factors of blue green algae problem including looking at contributing factors, causes and consequences. | A.1.1.1 Conduct desktop research and compile findings into a literature review. | Conduct desktop research and compile findings into a literature review. | [6 empty] | hypothesis matches theory | Does the research conducted and literature review confirm the hypothesis? Does the hypothesis fit with the project original goal? | Literature review completed | Develop and test a ‘fit-for-purpose’ small robot boat to clear blue/green algae faster than existing human methods can.
WATER | Develop and test a ‘fit-for-purpose’ small robot boat to clear blue/green algae faster than existing human methods can. | CRL 1: Initial idea and problem identification | A.1.1 Develop the hypothesis for the clearing of blue green algae for the yellow river catchment including addressing causal factors of blue green algae problem including looking at contributing factors and causes and consequences. | A.1.1.2 Conduct critical analysis on literature review and summarise findings to identify the hypothesis. | Conduct critical analysis on literature review and summarise findings to identify the hypothesis. | [6 empty] | N/A | Does the research conducted and literature review confirm the hypothesis? Does the hypothesis fit with the project original goal? | Hypothesis report completed | 0
WATER | Develop and test a ‘fit-for-purpose’ small robot boat to clear blue/green algae faster than existing human methods can. | CRL 1: Initial idea and problem identification | A.1.1 Develop the hypothesis for the clearing of blue green algae for the yellow river catchment including addressing causal factors of blue green algae problem including looking at contributing factors and causes and consequences. | A.1.1.3 Develop report looking at the yellow creek catchment including an EIS of the BG Algae. |  | Develop report looking at the yellow creek catchment including an EIS of the BG Algae. | [5 empty] | N/A | Does the research conducted and literature review confirm the hypothesis? Does the hypothesis fit with the project original goal? | EIS Report on Yellow creek
WATER | Develop and test a ‘fit-for-purpose’ small robot boat to clear blue/green algae faster than existing human methods can. | CRL 1: Initial idea and problem identification | A.1.2 Compile regulatory review of yellow creek area to identify Regulations, Standards and codes which would apply to the use of small boats within yellow creek. | A.1.2.1 Research yellow creek area council codes. | Research yellow creek area council codes. | [6 empty] | The project does not intend to break any codes or regulations, rather the process is for due diligence purposes mainly. | Does the research conducted and literature review confirm the hypothesis? Does the hypothesis fit with the project original goal? | N/A
WATER | Develop and test a ‘fit-for-purpose’ small robot boat to clear blue/green algae faster than existing human methods can. | CRL 1: Initial idea and problem identification | A.1.2 Compile regulatory review of yellow creek area to identify Regulations, Standards and codes which would apply to the use of small boats within yellow creek. | A.1.2.2 Contact local council member to discuss the use of small boats within Yellow creek. | Contact local council member to discuss the use of small boats within Yellow creek. | [6 empty] | The project does not intend to break any codes or regulations, rather the process is for due diligence purposes mainly. | Does the research conducted and literature review confirm the hypothesis? Does the hypothesis fit with the project original goal? | N/A
WATER | Develop and test a ‘fit-for-purpose’ small robot boat to clear blue/green algae faster than existing human methods can. | CRL 1: Initial idea and problem identification | A.1.2 Compile regulatory review of yellow creek area to identify Regulations, Standards and codes which would apply to the use of small boats within yellow creek. | A.1.2.3 Conduct due diligence on state and federal codes and compile a one page factsheet on how the small boats will comply or are not of concern to state and federal government codes. | Conduct due diligence on state and federal codes and compile a one page factsheet on how the small boats will comply or are not of concern to state and federal government codes. | [6 empty] | The project does not intend to break any codes or regulations, rather the process is for due diligence purposes mainly. | Does the research conducted and literature review confirm the hypothesis? Does the hypothesis fit with the project original goal? | One Page Regulations and Codes factsheet
WATER | Develop and test a ‘fit-for-purpose’ small robot boat to clear blue/green algae faster than existing human methods can. | CRL 2: Early stage research | A.2.1 Prepare a market comparison report for the project. | A.2.1.1 Conduct Market Research into the existing algae clearing tools world wide. |  | Conduct Market Research into the existing algae clearing tools world wide. | [5 empty] | N/A | Has the whole market been covered? | N/A
WATER | Develop and test a ‘fit-for-purpose’ small robot boat to clear blue/green algae faster than existing human methods can. | CRL 2: Early stage research | A.2.1 Prepare a market comparison report for the project. | A.2.1.2 Conduct research into all algae clearing techniques available currently in Australia and the world. |  | Conduct research into all algae clearing techniques available currently in Australia and the world. | [5 empty] | the research completed is the sound representation of the current state of algae clearing techniques in Australia including costs. | Have all techniques been considered for this project | N/A
WATER | Develop and test a ‘fit-for-purpose’ small robot boat to clear blue/green algae faster than existing human methods can. | CRL 2: Early stage research | A.2.2 Prepare a feasibility report on the small robot boat | A.2.2.1 Conduct research into the production of small boats including looking at materials and cost. |  | Conduct research into the production of small boats including looking at materials and cost. | [5 empty] | the research completed is the sound representation of the current state of algae clearing techniques in Australia including costs. | N/A | Feasibility Report Completed
WATER | Develop and test a ‘fit-for-purpose’ small robot boat to clear blue/green algae faster than existing human methods can. | CRL 2: Early stage research | A.2.2 Prepare a feasibility report on the small robot boat | A.2.2.2 Conduct a cost benefit analysis on the boat vs the potential algae clearing capability. |  |  | Conduct a cost benefit analysis on the boat vs the potential algae clearing capability. |  |  |  |  | N/A | Does the cost benefit analysis show that the small boat clearing method will be more cost effective AND more efficient at clearing algae than current methods used? | Complete Cost Benefit Analysis
WATER | Develop and test a ‘fit-for-purpose’ small robot boat to clear blue/green algae faster than existing human methods can. | CRL 3: Concept development | A.3.1 Collect and conduct testing based on what was reported from the Hypothesis Report, Feasibility Report and to ensure compliance with all codes and regulations and collect data to form baseline. | A.3.1.1 Measure the amount of green/blue algae within yellow creek through transit square. |  |  | Measure the amount of green/blue algae within yellow creek through transit square. |  |  |  |  | The testing conducted on the day represents the normal yellow creek state. | Does the transit square give a good enough representation of algae in yellow creek? | base line data records including pictures of yellow creek on the day of testing and test reports
WATER | Develop and test a ‘fit-for-purpose’ small robot boat to clear blue/green algae faster than existing human methods can. | CRL 3: Concept development | A.3.1 Collect and conduct testing based on what was reported from the Hypothesis Report, Feasibility Report and to ensure compliance with all codes and regulations and collect data to form baseline. | A.3.1.2 Collect and test water samples from yellow creek measuring turbidity and sediment suspension, Ph. level, oxygen saturation. |  |  | collect and test water samples from yellow creek measuring turbidity and sediment suspension, Ph. level, oxygen saturation. |  |  |  |  | The testing conducted on the day represents the normal yellow creek state. | Does the testing accurately represent yellow creek? Were the conditions of the testing appropriate for it to be deemed the normal standard? | base line data records including pictures of yellow creek on the day of testing and test reports
WATER | Develop and test a ‘fit-for-purpose’ small robot boat to clear blue/green algae faster than existing human methods can. | CRL 3: Concept development | A.3.1 Collect and conduct testing based on what was reported from the Hypothesis Report, Feasibility Report and to ensure compliance with all codes and regulations and collect data to form baseline. | A.3.1.3 Determine current ecological state of yellow lake including determining the amount of life forms and plant life within the yellow lake area. |  |  | determine current ecological state of yellow lake including determining the amount of life forms and plant life within the yellow lake area. |  |  |  |  | The testing conducted on the day represents the normal yellow creek state. | Does the testing accurately represent yellow creek? Were the conditions of the testing appropriate for it to be deemed the normal standard? | base line data records including pictures of yellow creek on the day of testing and test reports
WATER | Develop and test a ‘fit-for-purpose’ small robot boat to clear blue/green algae faster than existing human methods can. | CRL 3: Concept development | A.3.2 Produce a succinct 'Proof of concept' brief outlining the results from the data collection and reports conducted. | A.3.2.1 Use the completed Feasibility Report and the budget to create the 'proof of concept'. |  |  | Use the completed Feasibility Report and the budget to create the 'proof of concept'. |  |  |  |  | Proof of concept will be made up of existing reports and research with a thorough executive summary outlining key findings | Does the feasibility report provide enough information to create the 'prof of concept?' | Proof of concept
WATER | Develop and test a ‘fit-for-purpose’ small robot boat to clear blue/green algae faster than existing human methods can. | CRL 3: Concept development | A.3.2 Produce a succinct 'Proof of concept' brief outlining the results from the data collection and reports conducted. | A.3.2.2 Address the projects Budget and forecast how much money would be needed the entirety of the project, through to implementation. To be added in the 'Proof of concept' |  |  | Address the projects Budget and forecast how much money would be needed the entirety of the project, through to implementation. To be added in the 'Proof of concept' |  |  |  |  | Cost Benefit analysis will be used as a basis for the forecast budget | Do we have enough budget knowledge and information to confidently forecast how much the project will cost through to implementation phase? | Budget Report & Proof of Concept
WATER | Develop and test a ‘fit-for-purpose’ small robot boat to clear blue/green algae faster than existing human methods can. | CRL 3: Concept development | A.3.3 Build small robot boat prototype and test in a controlled remote environment | A.3.3.1 Source materials and construct boat prototype |  |  |  | Source materials and construct boat prototype |  |  |  | N/A | N/A | Photos of prototype development
WATER | Develop and test a ‘fit-for-purpose’ small robot boat to clear blue/green algae faster than existing human methods can. | CRL 3: Concept development | A.3.3 Build small robot boat prototype and test in a controlled remote environment | A.3.3.2 Seek initial test area, ensure it is a controlled remote environment. |  |  |  | Seek initial test area, ensure it is a controlled remote environment. |  |  |  | N/A | Is the test area and accurate representation of Yellow Creek conditions? | Photos of prototype testing
WATER | Develop and test a ‘fit-for-purpose’ small robot boat to clear blue/green algae faster than existing human methods can. | CRL 3: Concept development | A.3.3 Build small robot boat prototype and test in a controlled remote environment | A.3.3.3 Continuously collect data and compile initial prototype testing report. |  |  |  | Continuously collect data and compile initial prototype testing report. |  |  |  | prototype is somewhat successful and data can be collected | N/A | Prototype testing report

## 2. Project Budget
Expenditure Item (edit as necessary) | Y1 |  |  |  | Y1 Total | Y2 |  |  |  | Y2 Total | Grand Total
| Q1 | Q2 | Q3 | Q4 |  | Q1 | Q2 | Q3 | Q4
Develop and test a ‘fit-for-purpose’ small robot boat to clear blue/green algae faster than existing human methods can.
Direct employee expenses |  |  |  |  | 0 |  |  |  |  | 0 | 0
Internal contractors |  |  |  |  | 0 |  |  |  |  | 0 | 0
External contractors |  |  |  |  | 0 |  |  |  |  | 0 | 0
Communication, seminars, workshops, training |  |  |  |  | 0 |  |  |  |  | 0 | 0
Software licences / materials |  |  |  |  | 0 |  |  |  |  | 0 | 0
Motor vehicle expenses |  |  |  |  | 0 |  |  |  |  | 0 | 0
Travelling expenses |  |  |  |  | 0 |  |  |  |  | 0 | 0
Equipment purchases (less than $5000 each) |  |  |  |  | 0 |  |  |  |  | 0 | 0
Other - (please detail) |  |  |  |  | 0 |  |  |  |  | 0 | 0
Sub-total direct project expenditure | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
0
Direct employee expenses |  |  |  |  | 0 |  |  |  |  | 0 | 0
Internal contractors |  |  |  |  | 0 |  |  |  |  | 0 | 0
External contractors |  |  |  |  | 0 |  |  |  |  | 0 | 0
Communication, seminars, workshops, training |  |  |  |  | 0 |  |  |  |  | 0 | 0
Software licences / materials |  |  |  |  | 0 |  |  |  |  | 0 | 0
Motor vehicle expenses |  |  |  |  | 0 |  |  |  |  | 0 | 0
Travelling expenses |  |  |  |  | 0 |  |  |  |  | 0 | 0
Equipment purchases (less than $5000 each) |  |  |  |  | 0 |  |  |  |  | 0 | 0
Other - (please detail) |  |  |  |  | 0 |  |  |  |  | 0 | 0
Sub-total direct project expenditure | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Direct employee expenses |  |  |  |  | 0 |  |  |  |  | 0 | 0
Internal contractors |  |  |  |  | 0 |  |  |  |  | 0 | 0
External contractors |  |  |  |  | 0 |  |  |  |  | 0 | 0
Communication, seminars, workshops, training |  |  |  |  | 0 |  |  |  |  | 0 | 0
Software licences / materials |  |  |  |  | 0 |  |  |  |  | 0 | 0
Motor vehicle expenses |  |  |  |  | 0 |  |  |  |  | 0 | 0
Travelling expenses |  |  |  |  | 0 |  |  |  |  | 0 | 0
Equipment purchases (less than $5000 each) |  |  |  |  | 0 |  |  |  |  | 0 | 0
Other - (please detail) |  |  |  |  | 0 |  |  |  |  | 0 | 0
Sub-total direct project expenditure | 0 |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
Direct employee expenses |  |  |  |  | 0 |  |  |  |  | 0 | 0
Internal contractors |  |  |  |  | 0 |  |  |  |  | 0 | 0
External contractors |  |  |  |  | 0 |  |  |  |  | 0 | 0
Communication, seminars, workshops, training |  |  |  |  | 0 |  |  |  |  | 0 | 0
Software licences / materials |  |  |  |  | 0 |  |  |  |  | 0 | 0
Motor vehicle expenses |  |  |  |  | 0 |  |  |  |  | 0 | 0
Travelling expenses |  |  |  |  | 0 |  |  |  |  | 0 | 0
Equipment purchases (less than $5000 each) |  |  |  |  | 0 |  |  |  |  | 0 | 0
Other - (please detail) |  |  |  |  | 0 |  |  |  |  | 0 | 0
Sub-total direct project expenditure | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Project Administration total
Administration – Admin support employee expenses |  |  |  |  | 0 |  |  |  |  | 0 | 0
Administration- Office rental accommodation |  |  |  |  | 0 |  |  |  |  | 0 | 0
Administration- facilities and office equipment costs |  |  |  |  | 0 |  |  |  |  | 0 | 0
Administration- freight and postage |  |  |  |  | 0 |  |  |  |  | 0 | 0
Sub-total administration | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Capital expenditure (more than $5,000 each) |  |  |  |  | 0 |  |  |  |  | 0 | 0
Project direct expenditure total | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Project Administration total | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Project Capital expenditure total | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Project Grand total | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0

## LISTS (hidden)
Program Priority | Readiness Level
LAND | CRL 1: Initial idea and problem identification
WATER | CRL 2: Early stage research
Science & Knowledge | CRL 3: Concept development
CRL 4: Initial testing
CRL 5: Review and revision
CRL 6: Prototypes/trials improved significantly
CRL 7: Tested in a relevant environment
CRL 8: Substantial testing and data obtained
CRL 9: Wide-scale implementation ready
Beyond CRL 9 - Implementation Phase

## Sheet4 (hidden)
Project Outcome
Erosion Control on Central Islands by revegetating 3 Ha across 3 or more Islands | Erosion Control on Central Islands by revegetating 3 Ha across 3 or more Islands
Erosion Control on Central Islands by revegetating 3 Ha across 3 or more Islands | Feral Deer Management on Saibai and Boigu
Erosion Control on Central Islands by revegetating 3 Ha across 3 or more Islands | Reducing the Impact of Feral Pigs and Horses on Moa by undertaking control measures to reduce Horse populations by >70% and Pig populations by >35%
Erosion Control on Central Islands by revegetating 3 Ha across 3 or more Islands | 0
Erosion Control on Central Islands by revegetating 3 Ha across 3 or more Islands
Erosion Control on Central Islands by revegetating 3 Ha across 3 or more Islands
Erosion Control on Central Islands by revegetating 3 Ha across 3 or more Islands
Erosion Control on Central Islands by revegetating 3 Ha across 3 or more Islands
Erosion Control on Central Islands by revegetating 3 Ha across 3 or more Islands
Erosion Control on Central Islands by revegetating 3 Ha across 3 or more Islands
Erosion Control on Central Islands by revegetating 3 Ha across 3 or more Islands
Erosion Control on Central Islands by revegetating 3 Ha across 3 or more Islands
Erosion Control on Central Islands by revegetating 3 Ha across 3 or more Islands
Erosion Control on Central Islands by revegetating 3 Ha across 3 or more Islands
Erosion Control on Central Islands by revegetating 3 Ha across 3 or more Islands
Erosion Control on Central Islands by revegetating 3 Ha across 3 or more Islands
Erosion Control on Central Islands by revegetating 3 Ha across 3 or more Islands
Erosion Control on Central Islands by revegetating 3 Ha across 3 or more Islands
Erosion Control on Central Islands by revegetating 3 Ha across 3 or more Islands
Feral Deer Management on Saibai and Boigu
Reducing the Impact of Feral Pigs and Horses on Moa by undertaking control measures to reduce Horse populations by >70% and Pig populations by >35%
Reducing the Impact of Feral Pigs and Horses on Moa by undertaking control measures to reduce Horse populations by >70% and Pig populations by >35%
Reducing the Impact of Feral Pigs and Horses on Moa by undertaking control measures to reduce Horse populations by >70% and Pig populations by >35%
Reducing the Impact of Feral Pigs and Horses on Moa by undertaking control measures to reduce Horse populations by >70% and Pig populations by >35%
Reducing the Impact of Feral Pigs and Horses on Moa by undertaking control measures to reduce Horse populations by >70% and Pig populations by >35%
Reducing the Impact of Feral Pigs and Horses on Moa by undertaking control measures to reduce Horse populations by >70% and Pig populations by >35%
Reducing the Impact of Feral Pigs and Horses on Moa by undertaking control measures to reduce Horse populations by >70% and Pig populations by >35%
Reducing the Impact of Feral Pigs and Horses on Moa by undertaking control measures to reduce Horse populations by >70% and Pig populations by >35%
Reducing the Impact of Feral Pigs and Horses on Moa by undertaking control measures to reduce Horse populations by >70% and Pig populations by >35%
Reducing the Impact of Feral Pigs and Horses on Moa by undertaking control measures to reduce Horse populations by >70% and Pig populations by >35%
Reducing the Impact of Feral Pigs and Horses on Moa by undertaking control measures to reduce Horse populations by >70% and Pig populations by >35%
Feral Deer Management on Saibai and Boigu
Feral Deer Management on Saibai and Boigu
Feral Deer Management on Saibai and Boigu
Feral Deer Management on Saibai and Boigu
Feral Deer Management on Saibai and Boigu
Feral Deer Management on Saibai and Boigu
Feral Deer Management on Saibai and Boigu
Feral Deer Management on Saibai and Boigu
Feral Deer Management on Saibai and Boigu
Feral Deer Management on Saibai and Boigu